## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Kickoff and Repository Setup – Initialize GitHub repository, define folder structure, assign team roles and responsibilities. | MUST HAVE | No Dependency | Leena Gavande | 3- Completed
S1 | S1 | US-001 | Workflow Creation and Architecture Design – Design system architecture diagram showing data flow from API to ML to FastAPI to React frontend. | MUST HAVE | Lucid Chart / Draw.io | Gowthama R. | 3- Completed
S2 | S2 | US-001 | Agile Document Preparation – Prepare Product Backlog, Sprint Backlog, Stand-up, and Retrospection templates for Agile tracking. | MUST HAVE | No Dependency | Gowthama R. | 3- Completed
S2 | S2 | US-001 | Financial API Integration – Research and integrate Yahoo Finance / Alpha Vantage API to fetch historical stock and ETF price and volume data. | MUST HAVE | Yahoo Finance / Alpha Vantage API | Leena Gavande | 3- Completed
S2 | S2 | US-001 | Data Preprocessing Pipeline – Clean raw market data using Pandas: handle missing values, remove outliers, and engineer technical indicators. | MUST HAVE | Pandas, NumPy | Leena Gavande | 3- Completed
S3 | S3 | US-001 | ML Model Development – Train Random Forest and XGBoost models on historical data to classify Buy, Sell, and Hold signals with evaluation metrics. | MUST HAVE | Scikit-learn, XGBoost | Leena Gavande | 3- Completed
S4 | S4 | US-001 | FastAPI Backend Development – Design and build RESTful API endpoints for data retrieval, ML model inference, and signal delivery. | MUST HAVE | FastAPI, Uvicorn | Gowthama R. | 3- Completed
S5 | S5 | US-001 | ML and Backend Integration – Integrate preprocessing pipeline and ML model into FastAPI for real-time Buy/Sell/Hold signal prediction via /predict. | MUST HAVE | FastAPI, Scikit-learn, XGBoost | Gowthama R. | 3- Completed
S6 | S6 | US-001 | React Frontend Dashboard – Build interactive React dashboard with stock charts, signal display tables, and symbol/date-range filter controls. | MUST HAVE | React.js, Recharts, Axios | K. Ashok | 2- In Progress
S7 | S7 | US-001 | Frontend–Backend Integration – Connect React frontend to FastAPI backend using Axios API calls; handle CORS, loading states, and error responses. | MUST HAVE | React.js, FastAPI, CORS Middleware | K. Ashok | 2- In Progress
S8 | S8 | US-001 | Deployment and CI/CD – Deploy FastAPI backend on Render and React frontend on Vercel; configure GitHub Actions for automated CI/CD pipelines. | MUST HAVE | Render, Vercel, GitHub Actions | Karishma K. | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 102 | 16 | 7 | 10 | 4 | 8 | 5 | 6 | 4 | 6 | 3 | 5 | 8 | 6 | 14
SPRINT 1 BACKLOG
US-001 | T-01 | Project Kickoff – Initialize GitHub repo, define folder structure and assign team roles | 2026-02-02 | 2026-02-04 | Gowthama R. | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-02 | Workflow Creation – Design system architecture and data flow diagram using Draw.io | 2026-02-05 | 2026-02-07 | Gowthama R. | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-03 | Agile Document Preparation – Set up Product Backlog, Sprint Backlog, Stand-up, and Retrospection sheets | 2026-02-09 | 2026-02-09 | Gowthama R. | Others | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-04 | Financial API Research – Evaluate Yahoo Finance and Alpha Vantage APIs for data availability and rate limits | 2026-02-10 | 2026-02-11 | Leena Gavande | Others | 3- Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-05 | API Data Fetching – Write Python scripts to pull historical OHLCV data for stocks and ETFs | 2026-02-12 | 2026-02-13 | Leena Gavande | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-001 | T-06 | Data Preprocessing – Clean missing values, normalize data, and apply forward-fill for gaps using Pandas | 2026-02-16 | 2026-02-18 | Leena Gavande | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-07 | Feature Engineering – Compute technical indicators: RSI, MACD, Bollinger Bands, and Moving Averages | 2026-02-19 | 2026-02-21 | Leena Gavande | Coding | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0
US-001 | T-08 | Random Forest Model Training – Train and evaluate Random Forest classifier for Buy/Sell/Hold signal generation | 2026-02-23 | 2026-02-25 | Leena Gavande | Build | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
US-001 | T-09 | XGBoost Model Training – Train XGBoost model, tune hyperparameters, and compare accuracy with Random Forest | 2026-02-26 | 2026-02-27 | Leena Gavande | Build | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
SPRINT 3 BACKLOG
US-001 | T-10 | FastAPI Project Setup – Create FastAPI project structure with routers, schemas, and environment config | 2026-03-02 | 2026-03-03 | Gowthama R. | Build | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-11 | Prediction Endpoint – Implement /predict API endpoint that accepts stock symbol and returns Buy/Sell/Hold signal | 2026-03-04 | 2026-03-06 | Gowthama R. | Coding | 3- Completed | 6 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-12 | ML Pipeline Integration – Integrate data fetching, preprocessing, and model inference into single FastAPI pipeline | 2026-03-09 | 2026-03-13 | Gowthama R. | Integration Test | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-001 | T-13 | Dashboard UI Design – Create React wireframes and design layout for stock chart, signal table, and filter controls | 2026-03-16 | 2026-03-18 | K. Ashok | Design | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0
US-001 | T-14 | React Components – Build reusable components: stock price chart (Recharts), signal badge, and data table | 2026-03-19 | 2026-03-23 | K. Ashok | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 2 | 0
US-001 | T-15 | Filter Controls – Add stock symbol search and date range picker; wire filters to API query params | 2026-03-24 | 2026-03-27 | K. Ashok | Coding | 2- In Progress | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
SPRINT 5 BACKLOG
US-001 | T-16 | Frontend–Backend Integration – Connect React to FastAPI via Axios; resolve CORS issues and handle API errors | 2026-03-30 | 2026-03-31 | K. Ashok | Integration Test | 2- In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-17 | Backend Deployment – Deploy FastAPI on Render with environment variables; configure startup and keep-alive | 2026-03-30 | 2026-03-31 | Karishma K. | System Test | 2- In Progress | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-18 | Frontend Deployment – Deploy React app on Vercel; configure GitHub Actions CI/CD pipeline for auto-deploy | 2026-04-01 | 2026-04-01 | Karishma K. | System Test | 2- In Progress | 5 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-19 | End-to-End Testing and Documentation – Run full integration tests, fix bugs, and complete project documentation | 2026-04-02 | 2026-04-02 | Gowthama R., K. Ashok, Karishma K., Leena Gavande | System Test | 2- In Progress | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Unclear project scope and which financial APIs are most suitable. | Conducted team discussion and reviewed API documentation; selected Yahoo Finance for initial integration.
Sprint 1 | Day 4 | Uncertainty on architecture design – how ML model connects to backend. | Team brainstorming session held; architecture diagram created on Draw.io and approved by all members.
Sprint 2 | Day 6 | API rate limits encountered when fetching large historical datasets. | Implemented request throttling and caching in the data fetching script to stay within free-tier limits.
Sprint 2 | Day 8 | Missing values and inconsistent date formats in raw financial data. | Applied forward-fill, interpolation, and standardized date parsing using Pandas to resolve data quality issues.
Sprint 2 | Day 11 | Overfitting observed in initial XGBoost model during validation. | Applied cross-validation and hyperparameter tuning (learning rate, max depth) to regularize the model.
Sprint 3 | Day 14 | FastAPI routing conflict between /data and /predict endpoints. | Refactored API into separate router modules; each endpoint tested individually via Postman.
Sprint 4 | Day 18 | Recharts component causing rendering lag with large stock datasets. | Implemented data pagination and lazy loading in React; reduced initial payload size significantly.
Sprint 4 | Day 20 | CORS error blocking React frontend from accessing FastAPI backend. | Configured CORS middleware in FastAPI to allow the Vercel frontend origin domain.
Sprint 5 | Day 23 | Render free-tier backend timing out during cold starts. | Added keep-alive ping logic and optimized FastAPI startup time to reduce cold-start latency.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-13 | Gowthama R. | Documenting architecture decisions and API integration steps in GitHub Wiki. | Assuming requirements are clear without explicit team confirmation. | Conducting daily stand-ups and using GitHub for version control. | Created shared GitHub Wiki for project documentation; all teammates reviewed architecture diagram.
2 | Sprint 2 | 2026-02-16 | 2026-02-27 | Leena Gavande | Logging ML model training metrics (accuracy, F1-score) after each experiment run. | Pushing untested or undocumented code directly to the main branch. | Regular pair-programming and code review sessions with Gowthama R. | Implemented structured experiment logging; enforced PR review policy before merging to main.
3 | Sprint 3 | 2026-03-02 | 2026-03-13 | Gowthama R. | Writing API documentation using FastAPI Swagger UI and adding inline code comments. | Hardcoding configuration values and API keys directly in source code. | Modular code design and separation of concerns across backend routers. | Moved all configurations to .env files; Swagger UI auto-documentation activated and shared with team.
4 | Sprint 4 | 2026-03-16 | 2026-03-27 | K. Ashok | Adding loading spinners and error boundaries to all React API-dependent components. | Mixing API call logic directly inside UI components instead of separating into service files. | Component-based React architecture with reusable UI elements across the dashboard. | Refactored API calls into a dedicated services layer; loading and error states added to all components.
5 | Sprint 5 | 2026-03-30 | 2026-04-02 | Gowthama R, K. Ashok, Karishma K, Leena Gavande | Running end-to-end integration tests before each deployment to catch regressions early. | Waiting until the final sprint day to perform integration and deployment testing. | Agile sprint retrospectives, open team communication, and collaborative debugging sessions. | All integration tests passed; platform deployed successfully on Render and Vercel on schedule.